## Comparison
MOC workflows - Intelex out of the box vs Impala proposal
Out of the Box (Intelex)
Stage # | Stage Name | Complete | Replacement in Kind (Replacement in Kind = Yes) | Emergency (Emergency Change = Yes)
1 | Initiation | ✔ | ✔ | ✔
2 | Pre-Approval | ✔ | ✔ | ✔
3 | Evaluation | ✔ | — | —
4 | Design & Analysis | ✔ | — | ✔
5 | Implementation | ✔ | ✔ | ✔
6 | Start Up | ✔ | ✔ | ✔
7 | Follow Up | ✔ | ✔ | ✔
| Path (stage #) | 1-2-3-4-5-6-7 | 1-2-5-6-7 | 1-2-4-5-6-7
Replacement in Kind skips Evaluation and Design & Analysis; Emergency skips Evaluation (both decided at Pre-Approval).
Proposal (Impala - MOC Proposal Rev2)
Stage # | Stage Name | Complete | Simple (Simple Change = Yes) | Emergency (Emergency Change = Yes)
1 | Initiation | ✔ | ✔ | ✔
2 | Evaluation, Design & Analysis | ✔ | ✔ no checklist | —
3 | Approval | ✔ | ✔ | ✔
4 | Implementation | ✔ | ✔ | ✔
5 | Start Up | ✔ | ✔ | ✔
6 | Follow Up | ✔ | ✔ | ✔
| Path (stage #) | 1-2-3-4-5-6 | 1-2-3-4-5-6 | 1-3-4-5-6
Simple (replaces Replacement in Kind, for IT / organisational changes) keeps all stages but no Evaluation, D&A checklist; Emergency goes straight from Initiation to Approval.
Legend: | ✔ stage applies | — stage skipped | applies with differences

## Summary
MOC workflow - one workflow, three variants (Impala proposal, MOC Proposal Rev2)
Intelex configures ONE MOC workflow; the Emergency and Simple variants are paths/rules driven by the Initiation flags. Not three separate workflows (keeps the change within SOW 'Moderate configuration').
Stage # | Stage Name | Full MOC (Emergency = No, Simple = No) | Emergency (Emergency Change = Yes) | Simple (Simple Change = Yes) | Notes
1 | Initiation | Yes | Yes | Yes | Emergency: Emergency Justification [BA]. Simple: Change Type typically 4 (IT) or 5 (Org).
2 | Evaluation, Design & Analysis | Yes - checklist + tasks + D&A questions | SKIPPED - straight to Approval | Yes - NO checklist (tasks + D&A questions [TBC which]) | Emergency: retrospective completion? [TBC]. Simple: 'different process review' [TBC].
3 | Approval | Yes - sequential by Change Impact | Yes - who approves an emergency? [TBC] | Yes - sequential by Change Impact | Due 7 days (emergency due date [TBC]).
4 | Implementation | Yes | Yes | Yes - PSSR applicable? [TBC] | Entry only when Pre-Implementation tasks are closed.
5 | Start Up | Yes | Yes | Yes - applicable? [TBC]
6 | Follow Up | Yes | Yes - close only when regularised [TBC] | Yes | Entry only when Pre-Follow Up tasks are closed.
Open questions for the team
1. Emergency: who approves (Change Impact matrix as normal, or a single senior approver as in BRD RULE-B3-14)?
2. Emergency: is the Evaluation, D&A checklist completed retrospectively? Within how many days? Can the MOC close before?
3. Emergency: approval due date (shorter than 7 days?).
4. Simple: what is the 'different process review' for IT / organisational changes - does anything need capturing in Intelex?
5. Simple: which D&A and Implementation questions apply (alternatives, hazard assessment, PSSR, Start Up)?
6. Simple: confirm it keeps all 6 stages (Rev2) rather than skipping stages like the old 'Replacement in Kind'.
7. If both Emergency and Simple are Yes: which rule prevails (proposal: Emergency path, no checklist)?
Legend: grey = stage skipped; yellow = to be confirmed [TBC]; [BA] = BA proposal, not in Sam's Rev2.

## 1. Full MOC
Full MOC workflow (Emergency = No, Simple = No)
Proposal
Stage # | Stage Name | In this variant
1 | Initiation | Yes
2 | Evaluation, Design & Analysis | Yes
3 | Approval | Yes
4 | Implementation | Yes
5 | Start Up | Yes
6 | Follow Up | Yes
Detailed workflow (Intelex workbook format)
Stage # | Stage Name | Record Status | Stage Owner | Due Date | Workflow Buttons | Workflow Path | Email Template # | Comments
1 | Initiation | Initiation | Created By (Field) | N/A | Submit | If 'Emergency Change' = Yes: to 'Approval' Else: to 'Evaluation, Design & Analysis' | N01 | Recipient(s): Change Requester Mandatory: Location, Description, Emergency, Simple, Temporary, Change Type, Change Impact, Priority, Change Justification, Requested Change Date.
2 | Evaluation, Design & Analysis | Evaluation, Design & Analysis | MOC Coordinator (Role) | N/A | Submit | To 'Approval' | N01 | Recipient(s): Change Requester Checklist answered (not for Simple Change), D&A questions + justifications, documents attached.
[5 empty] | Roll Back | Back to 'Initiation' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
3 | Approval | Approval | MOC Coordinator (Role) | 7 days | Submit | To 'Implementation' | N01 / N08 | Recipient(s): Change Requester Mandated approvals by Change Impact, sequential Local > Regional > Global; ad hoc approvals allowed.
[5 empty] | Roll Back | If Emergency = Yes: back to 'Initiation' Else: back to 'Evaluation, Design & Analysis' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
4 | Implementation | Implementation | MOC Coordinator (Role) | N/A | Submit | To 'Start Up' | N01 | Recipient(s): Change Requester Entry only with Pre-Implementation tasks closed. PSSR, training, comms, installation, critical PSSR items.
[5 empty] | Roll Back | Back to 'Approval' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
5 | Start Up | Start Up | MOC Coordinator (Role) | N/A | Submit | To 'Follow Up' | N01 | Recipient(s): Change Requester Start-up completed, notes.
[5 empty] | Roll Back | Back to 'Implementation' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
6 | Follow Up | Follow Up | MOC Coordinator (Role) | N/A | Close |  | N04 | Recipient(s): Change Requester Entry only with Pre-Follow Up tasks closed. Temporary -> permanent MOC; Lessons Learnt.
[5 empty] | Roll Back | Back to 'Start Up' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
Workflow diagram

## 2. Emergency
Emergency variant (Emergency Change = Yes)
Proposal
Stage # | Stage Name | In this variant
1 | Initiation | Yes
2 | Evaluation, Design & Analysis | Skipped
3 | Approval | Yes - approver [TBC]
4 | Implementation | Yes
5 | Start Up | Yes
6 | Follow Up | Yes
Detailed workflow (Intelex workbook format)
Stage # | Stage Name | Record Status | Stage Owner | Due Date | Workflow Buttons | Workflow Path | Email Template # | Comments
1 | Initiation | Initiation | Created By (Field) | N/A | Submit | Emergency Change = Yes: straight to 'Approval' | N01 + N11 [BA] | Recipient(s): Change Requester, MOC Coordinator N11 alert to Terminal Manager + Regional HSEC [BA]. Emergency Justification mandatory [BA].
2 | Evaluation, Design & Analysis | - | - | - | - | SKIPPED | - | Retrospective completion of checklist / dossier? [TBC - BRD RULE-B3-14]
3 | Approval | Approval | MOC Coordinator (Role) | [TBC] (urgent) | Submit | To 'Implementation' | N01 / N08 | Recipient(s): Change Requester Approvals by Change Impact (as full flow) or single senior approver? [TBC]
[5 empty] | Roll Back | Back to 'Initiation' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
4 | Implementation | Implementation | MOC Coordinator (Role) | N/A | Submit | To 'Start Up' | N01 | Recipient(s): Change Requester Same as full flow.
[5 empty] | Roll Back | Back to 'Approval' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
5 | Start Up | Start Up | MOC Coordinator (Role) | N/A | Submit | To 'Follow Up' | N01 | Recipient(s): Change Requester Same as full flow.
[5 empty] | Roll Back | Back to 'Implementation' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
6 | Follow Up | Follow Up | MOC Coordinator (Role) | N/A | Close |  | N04 | Recipient(s): Change Requester Close only when the emergency dossier is regularised [TBC].
[5 empty] | Roll Back | Back to 'Start Up' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
Workflow diagram

## 3. Simple
Simple variant (Simple Change = Yes)
Proposal
Stage # | Stage Name | In this variant
1 | Initiation | Yes
2 | Evaluation, Design & Analysis | Yes - no checklist
3 | Approval | Yes
4 | Implementation | Yes
5 | Start Up | Yes - applicable? [TBC]
6 | Follow Up | Yes
Detailed workflow (Intelex workbook format)
Stage # | Stage Name | Record Status | Stage Owner | Due Date | Workflow Buttons | Workflow Path | Email Template # | Comments
1 | Initiation | Initiation | Created By (Field) | N/A | Submit | To 'Evaluation, Design & Analysis' | N01 | Recipient(s): Change Requester Simple Change = Yes (IT / organisational changes).
2 | Evaluation, Design & Analysis | Evaluation, Design & Analysis | MOC Coordinator (Role) | N/A | Submit | To 'Approval' | N01 | Recipient(s): Change Requester NO checklist generated. Tasks + D&A questions - which apply? [TBC]. 'Different process review' [TBC].
[5 empty] | Roll Back | Back to 'Initiation' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
3 | Approval | Approval | MOC Coordinator (Role) | 7 days | Submit | To 'Implementation' | N01 / N08 | Recipient(s): Change Requester Approvals by Change Impact, sequential (as full flow).
[5 empty] | Roll Back | Back to 'Evaluation, Design & Analysis' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
4 | Implementation | Implementation | MOC Coordinator (Role) | N/A | Submit | To 'Start Up' | N01 | Recipient(s): Change Requester PSSR applicable? [TBC]. Training + communication.
[5 empty] | Roll Back | Back to 'Approval' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
5 | Start Up | Start Up | MOC Coordinator (Role) | N/A | Submit | To 'Follow Up' | N01 | Recipient(s): Change Requester Applicable to IT / Org changes? [TBC]
[5 empty] | Roll Back | Back to 'Implementation' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
6 | Follow Up | Follow Up | MOC Coordinator (Role) | N/A | Close |  | N04 | Recipient(s): Change Requester Lessons Learnt.
[5 empty] | Roll Back | Back to 'Start Up' | N02 | Recipient(s): Change Requester
[5 empty] | Cancel |  | N03 | Recipient(s): Change Requester
Workflow diagram