## Read me
MOC Screening Question Setup - data load draft (Impala)
Source: 'MOC Proposal.xlsx' > 'Evaluation, D&A Checklist' (Sam Robinson, draft under review).
Columns follow the Intelex 'MOC Screening Question Setup' object (workbook Fields rows 279-293).
Part 1 (Universal) attached to the top location; Part 2 to the Liquids segment node; Part 3 to the Dry segment node.
Second 'J.' section in the source (Pre-Start-Up & Close-Out) renumbered as 'K.'; its items go to Start Up / Follow Up.
Blank filter = question generated regardless of that parameter (Intelex setup behaviour).
OPEN [TBC]: reduce the question set by Grade of Change (Minor short list / Major full list); answers Yes / No / N/A.
Intelex to confirm import template format before loading.

## Screening Questions
Item Number | Checklist Item | Category | MOC Workflow | WF Stages | Change Impacts (blank = all) | Emergency Change? (blank = always) | Temporary Change? (blank = always) | MOC Categories (blank = all) | Locations | Impala Remarks
10 | Verify that the proposed change falls within or outside the established Safe Operating Envelope (e.g. temperature, pressure, flow, instrument setpoints/alarms, control system logic/interlocks/PLC/DCS programming) | A. Initiation & Scope Definition | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
20 | Confirm the change type and duration; verify that temporary changes do not exceed approved duration or scope | A. Initiation & Scope Definition | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
30 | State all key control measures affected by the change and define additional control measures implemented to mitigate the increased risk | A. Initiation & Scope Definition | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
40 | New or modified equipment/infrastructure identified; user operational needs and deficiencies documented | A. Initiation & Scope Definition | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
50 | For all new operating systems or software installed — users have been consulted, system validated and documented, upload evidence | A. Initiation & Scope Definition | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
60 | Hazard evaluation performed during the Conceptualisation and Design phases | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
70 | Process Hazard Analysis (PHA) / HAZOP performed as appropriate to the scale and nature of the change, including review of: process fluid/material composition and characteristics, | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis | Moderate; Major |  |  |  | Impala (top level - all terminals) | Source note: 'Mandatory for Level 3+,' -> mapped to Moderate/Major [TBC]
80 | Major Accident Hazard (MAH) scenarios assessed and MARA updated where applicable | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
90 | Operational analysis/Task Risk Assessment completed to assess impact on normal and abnormal operations, human error and human factors should be accounted for within the assessments. | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
100 | Human factors review conducted | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
110 | Ergonomic hazards reviewed (excessive effort, repetitive movements, static/poor postures, manual handling of loads) | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
120 | New source of physical agents affecting health reviewed (noise, vibration, extreme temperatures, lighting, ionising radiation) | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
130 | New source of biological agents affecting health reviewed (fungi, bacteria, parasites) | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
140 | New handling of chemical substances identified; requirements for safe use defined, SDS Uploaded, reviewed and key control measures implemented in task risk assessment. SDS added to site register. | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
150 | Tertiary Containment Risk Assessment completed where applicable | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
160 | Review impacts to product quality | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
170 | Waste considerations identified and addressed — new types of solid waste, gaseous emissions, or liquid effluents produced or increased | B. Hazard Identification & Risk Assessment | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
180 | Engineering calculations or formal design review performed to verify process/integrity of the change | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
190 | Confirm system and component design meets relevant codes and standards, State the design codes applicable to this change. | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
200 | All affected mechanical equipment identified and impact assessed, meets standards, including: Piping Systems, Vessels (including Boilers), Rotating Equipment, Pumps | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
210 | Instrumentation and Electrical Systems (cables/trays) reviewed for impact from the change and meets the required standards | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
220 | New instrumentation/equipment requirements identified, impact assessed and meets required standard | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
230 | Process control parameters reviewed — new parameters introduced or existing ones modified; communication of impacts to other areas confirmed | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
240 | Emergency Equipment and Firefighting systems reviewed; fire protection equipment and emergency plans updated where required | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
250 | Review relevant drawings (P&IDs, Hazardous Area Classification, Underground Services, Tank Allocation, Fire Systems) | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
260 | Re-design completed where required for safety or process reasons | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
270 | Review and update Safety Critical Equipment records and Safety Critical Equipment List | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
280 | Lighting circuits: where construction or extension is required, specify number of luminaires, technical characteristics, and confirm compliance with minimum lighting levels for the work area | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
290 | Confirm proposed changes represent best practice | C. Engineering & Design Review | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
300 | Update or develop Operating Procedures and Maintenance Procedures, | D. Documentation & Drawing Updates | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
310 | Update or develop Process Documentation and Process Safety Information | D. Documentation & Drawing Updates | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
320 | Revision of drawings and as-built records | D. Documentation & Drawing Updates | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
330 | Verify that Safety Data Sheets (SDS) are current and accessible at the point of use | D. Documentation & Drawing Updates | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
340 | Update Chemical Inventory to reflect any new or changed substances | D. Documentation & Drawing Updates | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
350 | Update Regulatory documentation as required (e.g. COMAH Safety Report, Environmental Permits, Licenses, Consents, Contracts) | D. Documentation & Drawing Updates | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
360 | Update Plant Emergency Response Plan where affected by the change | D. Documentation & Drawing Updates | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
370 | Update Plant Inspection Schedules (including Tanks) where affected by the change | D. Documentation & Drawing Updates | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
380 | Identify and obtain all required Notifications, Official Permits, and Legal Licences prior to implementation | E. Regulatory, Permitting & Stakeholder Notifications | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
390 | Review all applicable Safety & Environmental Permits for required updates | E. Regulatory, Permitting & Stakeholder Notifications | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
400 | Notify competent authorities and relevant external stakeholders where required (e.g. HSE, Environmental Authority, Local Authority, Emergency Services) | E. Regulatory, Permitting & Stakeholder Notifications | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
410 | Review new regulations or standards required to govern use of spaces or equipment | E. Regulatory, Permitting & Stakeholder Notifications | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
420 | Review impacts on customers and notify where applicable | E. Regulatory, Permitting & Stakeholder Notifications | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
430 | Identify new spare parts required and update inventory in Ultimo | F. Maintenance, Spares & Asset Management | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
440 | Update Preventive Maintenance Plan and Plant Inspection Schedules to incorporate the change; confirm any additional locations or equipment added to the maintenance schedule | F. Maintenance, Spares & Asset Management | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
450 | Raise required Work Orders | F. Maintenance, Spares & Asset Management | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
460 | Identify where contractor personnel are required; ensure pre qualification questionnaire has been completed | G. Contractor Management | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
470 | Verify competencies and qualifications prior to commencement of work | G. Contractor Management | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
480 | Determine Lockout/Tagout (LOTO) requirements; confirm all lock points affected by the change have been identified and addressed | H. Permit to Work & Safe Work Controls | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
490 | Identify confined space work requirements — including any new confined spaces created by the change — and ensure appropriate permits and controls are in place | H. Permit to Work & Safe Work Controls | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
500 | Work at height requirements identified and controlled | H. Permit to Work & Safe Work Controls | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
510 | Lifting or hoisting equipment requirements identified and controlled | H. Permit to Work & Safe Work Controls | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
520 | Fixed stairs and/or platforms required — reviewed and designed appropriately | H. Permit to Work & Safe Work Controls | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
530 | Pedestrian or vehicular traffic patterns modified — controls defined; elements that could obstruct traffic or create fall hazards identified and guarded | H. Permit to Work & Safe Work Controls | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
540 | Moving parts exposed — guarding controls defined | H. Permit to Work & Safe Work Controls | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
550 | New hand and power tools required — certifications and training needs identified | H. Permit to Work & Safe Work Controls | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
560 | PPE requirements for the area reviewed; any modifications communicated to affected personnel | H. Permit to Work & Safe Work Controls | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
570 | Confirm all necessary controls for safe execution and evaluation of the change are defined and in place | H. Permit to Work & Safe Work Controls | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
580 | Communicate the change to all affected employees prior to implementation | I. Training & Communication | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
590 | Develop and deliver training and/or work instructions for affected employees (operator and maintenance); retain records of completed training prior to start-up | I. Training & Communication | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
600 | Organisational structure or staffing levels reviewed; modifications made to handle post-change operations | I. Training & Communication | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
610 | Personnel with business-critical roles introduced — legal profile, skills, induction and critical procedure knowledge verified | I. Training & Communication | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Impala (top level - all terminals)
620 | Essential Services Cyber Security Management System (CSMS) updated where applicable | J. IT/OT | Management of Change | Evaluation, Design & Analysis |  |  |  | 4. Change of Control Systems / IT / SIS | Impala (top level - all terminals)
630 | IACS / NIS cybersecurity procedures followed where control systems or industrial automation are affected | J. IT/OT | Management of Change | Evaluation, Design & Analysis |  |  |  | 4. Change of Control Systems / IT / SIS | Impala (top level - all terminals)
640 | Pre-Start-Up Safety Review (PSSR) completed and signed off before returning to service | K. Pre-Start-Up & Close-Out | Management of Change | Start Up |  |  |  |  | Impala (top level - all terminals)
650 | Verify all documentation, drawings, permits, and training records are complete and filed | K. Pre-Start-Up & Close-Out | Management of Change | Follow Up |  |  |  |  | Impala (top level - all terminals)
660 | Confirm all temporary changes have been closed out or formally extended within approved scope and duration | K. Pre-Start-Up & Close-Out | Management of Change | Follow Up |  |  | Yes |  | Impala (top level - all terminals)
670 | Confirm MOC is formally closed and all actions resolved; Action Plan (What / Who / When) completed for all items answered affirmatively during the checklist review | K. Pre-Start-Up & Close-Out | Management of Change | Follow Up |  |  |  |  | Impala (top level - all terminals)
10 | Toxicity, flammability, flash point, auto-ignition temperature, and static electricity hazards reviewed as part of PHA/HAZOP | Liquids Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Liquids (business segment)
20 | Pressure Reliefs and Vents reviewed for continued adequacy following the change | Liquids Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Liquids (business segment)
30 | Flame Arrestors and Detonation Traps reviewed for continued adequacy following the change | Liquids Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Liquids (business segment)
40 | Emergency Shutdown Systems and Safety Instrumented Systems (SIS/SIL) reviewed | Liquids Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Liquids (business segment)
50 | Fire Alarm and Detection Systems reviewed | Liquids Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Liquids (business segment)
60 | Tertiary containment and bunding reviewed; Tertiary Containment Risk Assessment completed | Liquids Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Liquids (business segment)
70 | Air Permit (VRU — Vapour Recovery Unit) reviewed and updated where applicable | Liquids Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Liquids (business segment)
80 | Wastewater Permit, Stormwater Permit, and Hazardous Waste consents reviewed and updated where applicable | Liquids Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Liquids (business segment)
90 | Tactical/Regional/Crisis/Global Emergency Information Packs updated where applicable | Liquids Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Liquids (business segment)
10 | New source of chemical agents affecting health reviewed (dust, gases, vapours, metallic fumes, mists) — particularly dust generation hazards specific to dry bulk handling | Dry Goods Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Dry (business segment)
20 | New types of liquid effluents produced or existing ones increased — reviewed where dry goods processing generates run-off (e.g. washing, leaching) | Dry Goods Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Dry (business segment)
30 | Combustible dust explosion risk assessed where dry bulk materials are handled or stored | Dry Goods Storage Supplement | Management of Change | Evaluation, Design & Analysis |  |  |  |  | Dry (business segment)